## Instructions
Transformation Health Self-Assessment
Is Your Transformation On Track or Heading for Trouble?
HOW TO USE THIS ASSESSMENT:
1. Go to the 'Assessment' tab
2. For each of the 10 dimensions, rate your project on a scale of 1-5:
• 5 = Strong (no concerns, well-managed)
• 4 = Good (minor gaps, manageable)
• 3 = At Risk (notable issues, needs attention)
• 2 = Struggling (significant problems, urgent action needed)
• 1 = Critical (major failure risk, immediate intervention required)
3. Be honest. This is for your benefit - inflating scores only delays addressing real issues.
4. Your total score and interpretation will calculate automatically
5. Go to the 'Results' tab to see what your score means and recommended next steps
WHAT MAKES A GOOD ASSESSMENT:
✓ Involve 2-3 key people (PM, Sponsor, Delivery Lead) and compare scores
✓ Take 10-15 minutes per person - don't rush
✓ Discuss where you scored differently and why
✓ Focus on evidence, not hope: 'Are we doing this?' not 'Could we do this?'
✓ Use the red flag indicators to calibrate your scoring
CONFIDENTIALITY:
Your responses are private. Rainman Advisory does not see your scores unless you choose to share them.
Questions? Contact Dave Lockley: dave@rainmanadvisory.com.au

## Self-Assessment
Transformation Health Assessment
Rate each dimension from 1 (Critical) to 5 (Strong). Enter scores in column B.
1. Strategic Clarity & Scope | 0 | Score 1-5
✓ Clear objectives, defined scope, no mission drift, success criteria measurable
🚩 Red Flags: Multiple versions of 'the plan', scope keeps expanding, buzzword objectives
2. Governance & Accountability | 0 | Score 1-5
✓ Active sponsor, clear escalation paths, regular steering, documented roles
🚩 Red Flags: Meetings get cancelled, decisions take weeks, same issues discussed repeatedly
3. Realistic Planning & Scheduling | 0 | Score 1-5
✓ Plans based on capacity, includes contingency, dependencies managed, team believes achievable
🚩 Red Flags: Timeline dictated by presentation date, 'we'll make up time later', no buffer
4. Resources & Capability | 0 | Score 1-5
✓ Key roles filled, people have capacity, skills gaps addressed, no single-person dependencies
🚩 Red Flags: 'We'll resource that later', key people at 60+ hours/week, single points of failure
5. Risk Identification & Management | 0 | Score 1-5
✓ Active risk register, top 10 have mitigation plans, early warnings tracked, honest discussion
🚩 Red Flags: Risk register created once and forgotten, same risks amber for months, leadership surprised
6. Financial Control & Benefits Tracking | 0 | Score 1-5
✓ Realistic budget, spend tracked, benefits have KPIs with baselines, owners identified
🚩 Red Flags: Contingency 80% depleted, benefits lack quantification, benefits measurement starts at go-live
7. Stakeholder Alignment & Communication | 0 | Score 1-5
✓ Stakeholder map exists, regular structured comms, feedback loops, consistent messaging
🚩 Red Flags: 'They don't need to know yet', executives hear different versions, surprises common
8. Change Management & Adoption Readiness | 0 | Score 1-5
✓ Impact assessed, training planned and resourced, adoption metrics defined, resistance managed
🚩 Red Flags: 'Change = communications', training planned 2 weeks before go-live, assume people will adapt
9. Delivery Execution & Quality | 0 | Score 1-5
✓ Clear definition of done, quality gates enforced, progress verified, comprehensive testing
🚩 Red Flags: '95% complete' for months, quality issues in production, testing compressed, team burning out
10. Dependencies & Integration Management | 0 | Score 1-5
✓ Dependencies mapped, integration points tested early, resource conflicts resolved, handoffs clear
🚩 Red Flags: 'Not our problem', integration tested at go-live, fighting for shared resources
TOTAL SCORE | 0 | out of 50
YOUR STATUS
INCOMPLETE - Enter all scores
→ Go to the 'Results' tab to see what this means and recommended next steps

## Results
Your Results & Recommendations
WHAT YOUR SCORE MEANS
40-50: HEALTHY TRANSFORMATION
Your project is well-managed with strong fundamentals. You're in the top quartile.
Consider a Health Check to:
• Validate your approach with independent perspective
• Identify opportunities to accelerate or strengthen controls
• Provide stakeholder assurance that things are truly on track
• Capture lessons learned for future initiatives
30-39: AT RISK - NEEDS ATTENTION
Your project has notable gaps that could escalate. 70% of transformations in this range
experience delays or cost overruns.
A Health Check can:
• Pinpoint the 2-3 highest-priority fixes
• Provide practical recommendations to course-correct
• Give evidence-based talking points for securing additional support
• Prevent small issues from becoming major problems
20-29: STRUGGLING - URGENT ACTION REQUIRED
Your project shows signs of significant distress. Without intervention, you're at high risk
of failure.
A Health Check will:
• Provide honest, independent assessment of where you stand
• Identify root causes (not just symptoms)
• Deliver action plan with prioritized remediation steps
• Help determine if project should continue, reset, or stop
BELOW 20: CRITICAL - IMMEDIATE INTERVENTION NEEDED
Your project is in crisis. Failure rate for projects in this range exceeds 80%.
You need immediate, independent support to:
• Assess whether the project can be saved or should be stopped
• Identify the most critical issues preventing progress
• Develop rapid stabilization plan
• Provide executive-level recommendations with clear options
RECOMMENDED NEXT STEPS
1. SHARE YOUR RESULTS (Recommended)
Get a free 30-minute discussion with an independent transformation expert.
• Review your scores and identify top 3 priorities
• Learn what works in similar situations
• Discuss whether formal Health Check makes sense
• Get immediate, practical guidance you can act on this week
No obligation. Just honest expert input.
Email: dave@rainmanadvisory.com.au
2. TAKE ACTION YOURSELF
• Review your Assessment tab - which dimensions scored lowest?
• Prioritize the 3 most critical gaps
• Build a 30-day action plan to address them
• Re-assess in 4-6 weeks to measure improvement
3. COMMISSION A FORMAL HEALTH CHECK
If your score was below 30, or you have multiple dimensions scoring 1-2:
What you get:
• 3-7 day independent review of your transformation
• Evidence-based assessment across all 10 dimensions
• Clear RAG (Red/Amber/Green) status executives can trust
• Prioritized action plan with practical next steps
• Peace of mind that issues surface before they escalate
Investment: Fixed-fee based on scope
Contact: dave@rainmanadvisory.com.au
WHY INDEPENDENT ASSESSMENT MATTERS
You're too close to see clearly. When running a transformation day-to-day, it's hard to:
• Distinguish real progress from activity
• Challenge optimistic reporting without seeming negative
• Spot patterns you've never encountered before
• Know if what you're experiencing is normal or a warning sign
An independent Health Check gives you:
✓ Objective perspective from someone who's seen hundreds of transformations
✓ Ability to surface issues without political consequences
✓ Benchmarking against what 'good' actually looks like
✓ Evidence to support requests for time, money, or resource adjustments
✓ Stakeholder confidence that expert has verified your approach
About This Assessment:
Based on the Rainman Advisory Transformation Assurance framework, developed through 25+ years
of transformation delivery and assurance across financial services, government, and corporate sectors.
The 10 dimensions represent the most common failure modes across hundreds of transformation projects.
Contact: Dave Lockley ¦ dave@rainmanadvisory.com.au ¦ www.rainmanadvisory.com.au